## Overall Progress
MHOKM Progress Dashboard
Milestone | Percentage Completion
Front End | 90%
Backend | 98%
API Integration | 35%
Overall Project Progress | 74.33%

## Tasks Flow
MHOKM Progress
Super Admin Flow
Sr.No | Detailed Feature | Front End | Backend | API Integration | Testing
1 | Login Screen | Completed | Completed | Completed | Completed
2 | Sign Up | Completed | Completed | In Progress | Completed
3 | Forget Password | Completed | Completed | In Progress | Completed
4 | Dashboard | Completed | In Progress | In Progress | Completed
5 | Dashboard Request | Completed | Completed | In Progress | Completed
6 | Request view Details | Completed | Completed | In Progress | Completed
7 | Meeting Request | Completed | Completed | In Progress | Completed
8 | Meeting view details | Completed | Completed | In Progress | Completed
9 | Report Page | Completed | Completed | In Progress | Completed
10 | Admin Page Design - Administration & Dept Creation | Completed | Completed | Completed | Completed
11 | Add new ticket | Completed | Completed | In Progress | Completed
12 | admin listing | Completed | Completed | Completed | Completed
13 | theme setting | Completed | Completed | Completed | Completed
| Total Tasks | 10 | 10 | 10 | 4
Percentage Completion |  | 100% | 98% | 43% | 100%
Admin Flow
Sr.No | Detailed Feature | Front End | Backend | API Integration | Testing
1 | Dashboard Screen | Completed | In Progress | Not Started | In Progress
2 | Dashboard Request Screen | Completed | Completed | Not Started | In Progress
3 | Request View Details | Completed | Completed | Not Started | In Progress
4 | Add Unit | Completed | Completed | Completed | In Progress
6 | Update Unit/Edit details | Completed | Completed | Completed | In Progress
7 | Add Unit Members | Completed | Completed | Completed | In Progress
8 | Update Unit Members | Completed | Completed | Not Started | In Progress
9 | Meeting Request | Completed | Completed | Completed | In Progress
10 | Meeting View Details | Completed | Completed | Completed | In Progress
11 | Committee Request | Completed | Completed | Not Started | In Progress
12 | Committee Review Details | Completed | Completed | Not Started | In Progress
13 | Admin KPIs Request form | Completed | Completed | Not Started | In Progress
14 | KPIs request review Details | Completed | Completed | Not Started | In Progress
15 | Settings Screen | Completed | Completed | Not Started | In Progress
16 | Theme Settings | Completed | Completed | Completed | In Progress
17 | Admin IPOM Request | Completed | Completed | In Progress | In Progress
Percentage Completion |  | 100% | 98% | 13% | 23%
Team/Unit Lead Flow
Sr.No | Detailed Feature | Front End | Backend | API Integration | Testing
1 | Dashboard Screen | Completed | Completed | In Progress | In Progress
2 | Dashboard Request Screen | Completed | Completed | In Progress | In Progress
3 | Request View Details | Completed | Completed | In Progress | In Progress
4 | Add new member | Completed | Completed | In Progress | In Progress
5 | Assign Tasks | Completed | Completed | In Progress | In Progress
6 | View Task Details | Completed | Completed | Not Started | Not Started
7 | Meeting Request | Completed | Completed | Not Started | Not Started
8 | Meeting View Details | Completed | Completed | Not Started | Not Started
9 | Committee Request | Completed | Completed | Not Started | Not Started
10 | Committee Review Details | Completed | Completed | Not Started | Not Started
11 | Admin KPIs Request form | Completed | Completed | Not Started | Not Started
12 | KPIs request review Details | Completed | Completed | Not Started | Not Started
13 | Settings Screen | Completed | Completed | Not Started | Not Started
14 | Theme Settings | Completed | Completed | Not Started | Not Started
15 | Admin IPOM Request | Completed | Completed | Not Started | Not Started
16 | Engagement Tool | Completed | Completed | Not Started | Not Started
17 | Gating Committee | Completed | Completed | Not Started | Not Started
18 | Phase Request Description | Completed | Completed | Not Started | Not Started
19 | Phase request Success | Completed | Completed | Not Started | Not Started
20 | Phase Request Impact | Completed | Completed | Not Started | Not Started
21 | Phase Request Stakeholders | Completed | Completed | Not Started | Not Started
22 | Phase request DataFeasibility | Completed | Completed | Not Started | Not Started
Percentage Completion |  | 100% | 100% | 0% | 0%
User Flow
Sr.No | Detailed Feature | Front End | Backend | API Integration | Testing
1 | User Register | Completed | Completed | Not Started | Not Started
2 | User Login | Completed | Completed | Not Started | Not Started
3 | User Forget Password | Completed | Completed | Not Started | Not Started
4 | Password Reset Screen | Completed | Completed | Not Started | Not Started
5 | View Task Details | Completed | Completed | Not Started | Not Started
6 | Home Page Dashboard | Completed | Completed | Not Started | Not Started
7 | Phase request Success | Completed | Completed | Not Started | Not Started
8 | Settings | Completed | Completed | Not Started | Not Started
Percentage Completion |  | 100% | 100% | 0% | 0%
Analytics Team Flow
Sr.No | Detailed Feature | Front End | Backend | API Integration | Testing
1 | User Register | Completed | Completed | Not Started | Not Started
2 | User Login | Completed | Completed | Not Started | Not Started
3 | Analytics Lead | Completed | Completed | Not Started | Not Started
4 | Analytics Team Member | Completed | Completed | Not Started | Not Started
5 | Team Lead View Details | Completed | Completed | Not Started | Not Started
6 | Analytics Team Lead - Dashboards Review | Completed | Completed | Not Started | Not Started
7 | Request View Details | Completed | Completed | Not Started | Not Started
Percentage Completion |  | 100% | 100% | 0% | 0%