## Super Admin
[5 empty] | Untested | 0
[5 empty] | Pass | 22
[5 empty] | Fail | 28
[5 empty] | Blocked | 0
PROJECT NAME: | MHOKM
MODULE NAME: | Super Admin
EXECUTED BY: | Ali Shozab
DATE: | 2024-05-08
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Super Admin
landing page text error |  | 1.open app and come on Landing page 2. See text | Enter your email and password to login | Enter your name and email to login | Fail
Email and password Validation |  | 1.open app and come on Landing page 2. See email and password field | Email and password should required and valid | Email and password should required and valid | Pass
Forget Password? |  | 1.open app and come on Landing page 2. click on Forget password. 3. enter email and send OTP. 4. Enter new password. | Password should changed. | Password will not changed. | Fail
Sign in with google |  | 1.open app and click on google logo | Super admin should login | Super admin will not login | Fail
Sign in with facebook |  | 1.open app and click on facebook logo | Super admin should login | Super admin will not login | Fail
Don't have an account |  | 1.open app and click on don't have an account. 2. fill form and rejister. | Super admin should rejister | Super admin will not rejister | Fail
Select Admin or Team Lead on login page |  | 1. open app and choose admin or team lead login. | user should login as a selected profile.
Login |  | 1.open app and come on Landing page 2. enter email and password to login. | Super admin should login | Super admin will login | Pass
Phases Request |  | 1. after login below dashboard phases request. | Request phase tab should be there. | it will not there. | Fail
Dashboard view after login |  | 1.After login new screen open. | After login dashboard screen should appear as per figma design | After login dashboard screen will not appear as per figma design and it open dashboard requests page | Fail
Dashboard requests after login |  | 1.open app and see dashboard requests from dashboard. | Requests should appear. | Request will appear. | Pass
View dashboard requests phases |  | 1.open app and see dashboard requests forms from dashboard. | It should show 3 phases as per figma. | it will show from as per figma | Pass
View dashboard requests today request list |  | 1.open app and see dashboard requests forms from dashboard. | it should show today request. | it will show today request. | Pass
View dashboard requests pending request list |  | 1.open app and see dashboard pending requests forms from dashboard. | it should show pending request. | it should will pending request. | Pass
View dashboard requests completed request list |  | 1.open app and see dashboard requests forms from dashboard. | it should show completed request. | it will show completed request. | Pass
Meeting section and select searchbar. |  | 1. open App 2. open meeting section and search in search field. | it should search the required result. | it will not search. | Fail
Meeting section. |  | 1.open app and see meeting requests forms from meeting section. | it should show meetings | it should show meetings | Pass
Meeting section and selection of meeting (Approve/Denied) |  | 1.open app and see meeting requests forms from meeting section. 2.View meetings info and accept or delete the meetings. | it should show meeting info and accept or delete meeting request. | it will show meeting info and accept or delete meeting request. | Pass
Meeting denied accept coment. |  | 1.open app and see meeting requests forms from meeting section. 3.View meetings info and delete the meetings. After deletion text box appear form reason. | it should accept text in text field. | it will not accept text in text field. | Fail
Meeting section. |  | 1.open app and see meeting requests forms from meeting section.2. there are 4 tabs in figma. | it should show 4 tabs as per figma i.e. today,pending,approved,cancelled. | it will not show 4 tabs as per figma. | Fail
Select user and select department. |  | 1. open app and select user. 2. Select Department. | it shouldbe selected. | it will not selected. | Fail
Select user and select searchbar |  | 1. open app and select user. 2. write in search bar. | it should search the required result. | it will not search. | Fail
Select user section. |  | 1. select user section to see the list of users. | it should show users list | it will show users list | Pass
user edit,view and delete in user section. |  | 1. select user section and edit,delete and view user. | it should work on specific command. | it will work on specific command. | Pass
user delete in user section. |  | 1. select user section and delete user. | it should delete user. | it will delete user but problem in refresh state | partial
active/inactive status in user section |  | 1. select user section and inactive/active user status. | it should change user status | it will not change user status | Fail
Open user section and see page filter. |  | 1. select user section and see page filter. | it should show page filter. | it will not show page filter. | Fail
Open report section and filter data |  | 1. select report section and filter data | it should filter the data. | it will filter data. | Pass
Open report section and export as PDF. |  | 1. select report section and click export button. | it should export PDF. | it will not export PDF. | Fail
Open report section and see page filter. |  | 1. select report section and see page filter. | it should show page filter. | it will not show page filter. | Fail
open add admin. |  | 1. select add admin and see the rejistered admin. | it should show rejistered admin. | it will show rejistered admin. | Pass
open add admin and select active/inactive admin status. |  | 1. select add admin and change the rejistered admin .status. | its should change the rejistered admin status | its will not change the rejistered admin status | Fail
open add admin and click on view to see the admin detail. |  | 1. select add admin and view the rejistered admin .status. | it should show admin data. | it will not show admin data and fields are empty | Fail
open add admin and click on view to see the admin details and use cancel button. |  | 1. select add admin and view the rejistered admin and click cancel button. | it should close menu. | it will not working. | Fail
open add admin and click on edit to edit the admin details and use update button.. |  | 1. select add admin and edit the rejistered admin and click update button. | it should update info. | it will not update info. | Fail
open add admin and click on delete to delete the admin. |  | 1. select admin and delete the rejistered admin and click delete button. | it should delete admin. | it will not delete admin. | Fail
open add admin and see the admin department. |  | 1. open admin and view the admin department | it should show deparment. | it will not show deparment. | Fail
add admin after give details. |  | 1.open admin and add admin 2. give admin details and submit. | it should show succes pop up as figma | it will not show succeed pop up and admin will create. | Fail
Open add admin section and export as PDF. |  | 1. select add admin section and click export button. | it should export PDF. | it will not export PDF. | Fail
Open add admin section and see page filter. |  | 1. select add admin section and see page filter. | it should show page filter as per figma. | it will not show page filter. | Fail
Open add admin section and see header. |  | 1. select add admin section and see in hearder. 2. select Search and "+" | it should show on web as per figma. | it will not show | Fail
open setting and upload picture from gallery. |  | select setting and click on image icon. | it should get picture from device and upload it. | it should get picture from device and can not upload it. | Fail
open setting and change colour theme. |  | select setting and click any colour from given colours. | it should change colour. | it will change colour. | Pass
open setting and enter text in text fields. |  | select setting and click on input field . | it should accept text in text field. | it will accept text in text field. | Pass
open setting and check check password icon |  | select setting and click on show password icon. | it should show password. | it will show password. | Pass
open setting and update password. |  | select setting and click on update password button.. | it should update password. | it will not update password. | Fail
logout button |  | click on logout. | it should logout account. | it will logout account. | Pass
Pass
Pass
Pass
Pass
Pass

## Admin
[5 empty] | Untested | 0
[5 empty] | Pass | 76
[5 empty] | Fail | 0
[5 empty] | Blocked | 0
PROJECT NAME: | MHOKM
MODULE NAME: | Admin |  | Total Passed | 5
EXECUTED BY: | Ali Shozab |  | Total Failed | 0
DATE: | 2024-08-12
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Signin |  | 1.open app and landing page sign in appear. 2. Enter your valid email and password. | it should accept email |  | Pass
signin with google |  | 1.open app and landing page sign in appear. 2.Click on google icon to signin with google. | it should login with google. |  | Pass
signin with facebook. |  | 1.open app and landing page sign in appear. 2.Click on facebook icon to signin with facebook. | it should login with facebook. |  | Pass
Forget Password? |  | 1.open app and landing page sign in appear. 2.Click on forget password. | Password should be reset. |  | Pass
Landing page |  | 1.After sign in. 2. Landing page screen. | It should show responsive dashboard. |  | Pass
Search text field. |  | 1.After sign in. 2. On Landing page screen search field will search the result. | It should search the required result. |  | Pass
Date Filter search |  | 1.After sign in. 2. On Landing page screen date filter search the result. | It should search the required result. |  | Pass
Total forms graph is searchable. |  | 1.After sign in. 2. On Landing page screen search total forms data. | It should search the required result. |  | Pass
Adminitration and department searchable |  | 1.After sign in. 2. On Landing page screen department choose picklist. | It should search the required result. |  | Pass
Landing page "+" sign |  | 1.After sign in. 2. On Landing page screen click "+" . | It should perform its function. |  | Pass
Notification |  | 1.After sign in. 2. On Landing page screen click notification. | It should show notifications. |  | Pass
Dashboard request. |  | 1.After sign in. 2. click on dashboard. | it should show dashboard today requests. |  | Pass
Search text field. |  | 1.After sign in. 2. On dashboard screen search field will search the result. | It should search the required result. |  | Pass
Dashboard approved request. |  | 1.After sign in. 2. click on dashboard. | it should show dashboard approved requests. |  | Pass
Dashboard pending request. |  | 1.After sign in. 2. click on pending dashboard requests. | it should show dashboard pending requests. |  | Pass
Dashboard rejected request. |  | 1.After sign in. 2. click on rejected dashboard requests. | it should show dashboard rejected requests. |  | Pass
Dashboard request view form. |  | 1.After sign in. 2. click on today dashboard requests. 3. View details. | it should show form details. |  | Pass
Dashboard accept request. |  | 1.After sign in. 2. click on today dashboard requests. 3. View details. 4. click on accept button. | it should accept request and pop up menu appear Dashboard request approved. |  | Pass
Dashboard reject form |  | 1.After sign in. 2. click on today dashboard requests. 3. View details. 4. click on reject button. | it should rejectt request and pop up menu appear Dashboard request rejected and enter reason or click on send. |  | Pass
KPI request. |  | 1.After sign in. 2. click on dashboard. | it should show KPI today requests. |  | Pass
KPI today request. |  | 1.After sign in. 2. click on dashboard. | it should show KPI approved requests. |  | Pass
KPI pending request. |  | 1.After sign in. 2. click on pending KPI requests. | it should show KPI pending requests. |  | Pass
KPI rejected request. |  | 1.After sign in. 2. click on rejected KPI requests. | it should show KPI rejected requests. |  | Pass
KPI request view form. |  | 1.After sign in. 2. click on today KPI requests. 3. View details. | it should show form details. |  | Pass
KPI accept request. |  | 1.After sign in. 2. click on today KPI requests. 3. View details. 4. click on accept button. | it should accept request and pop up menu appear KPI request approved. |  | Pass
KPI reject form |  | 1.After sign in. 2. click on today KPI requests. 3. View details. 4. click on reject button. | it should reject request and pop up menu appear KPI request rejected and enter reason or click on send. |  | Pass
Ticketing request. |  | 1.After sign in. 2. click on dashboard. | it should show ticketing today requests. |  | Pass
Ticketing approved request. |  | 1.After sign in. 2. click on dashboard. | it should show ticketing approved requests. |  | Pass
Ticketing pending request. |  | 1.After sign in. 2. click on pending ticketing requests. | it should show ticketing pending requests. |  | Pass
ticketing rejected request. |  | 1.After sign in. 2. click on rejected ticketing requests. | it should show ticketing rejected requests. |  | Pass
Ticketing request view form. |  | 1.After sign in. 2. click on today ticketing requests. 3. View details. | it should show form details. |  | Pass
ticketing accept request. |  | 1.After sign in. 2. click on today ticketing requests. 3. View details. 4. click on accept button. | it should accept request and pop up menu appear ticketing request approved. |  | Pass
ticketing reject form |  | 1.After sign in. 2. click on today ticketing requests. 3. View details. 4. click on reject button. | it should reject request and pop up menu appear ticketing request rejected and enter reason or click on send. |  | Pass
Click on add team |  | 1.After sign in. 2. click on add team. | it should show rejistered team members information. |  | Pass
Team staus change |  | 1.After sign in. 2. click on add team 3. Admin change the member status as ACTIVE.INACTIVE | it should change according to given instruction |  | Pass
view team member information. |  | 1.After sign in. 2. click on add team. 3. Click on pencil to see the required member information. 4. click update button to update the information. | it should edit the member information. |  | Pass
edit team member information. |  | 1.After sign in. 2. click on add team. 3. Click on eye icon to see the required member information. | it should show the member information. |  | Pass
delete team member information. |  | 1.After sign in. 2. click on add team. 3. Click on delete icon to see the required member information. | it should delete the member information. |  | Pass
export team members list. |  | 1.After sign in. 2. click on add team. 3. Click on export PDF | it should export pdf of team members. |  | Pass
add team members |  | 1.After sign in. 2. click on add team. 3. Click on add team button. | it should take input as information of team member and rejistered it. |  | Pass
Click on meetings |  | 1.After sign in. 2. click on meeting | it should show today meetings request. |  | Pass
Click on meetings |  | 1.After sign in. 2. click on meeting. 3. click on approved meeting. | it should show approved meetings. |  | Pass
Click on meetings |  | 1.After sign in. 2. click on meeting. 3. click on rejected meeting. | it should show rejected meetings. |  | Pass
view meeting information. |  | 1.After sign in. 2. click on meetings 3. Click on view details and accept or reject option there. | it should only work decision buttons. |  | Pass
accept meeting. |  | 1.After sign in. 2. click on meetings 3. Click on accept. | it should accept meetings. |  | Pass
Reject meeting. |  | 1.After sign in. 2. click on meetings 3. Click on reject. | it should reject meetings and take reason and click on send. |  | Pass
change colour Settings |  | 1. Click on settings. 2. click on any colour. | it should change the selected colour. |  | Pass
Change password |  | 1. Click on settings. 2. enter current password and enter new password. 3. click on update form. | it should update password. |  | Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass

## Analytical
[5 empty] | Untested | 0
[5 empty] | Pass | 19
[5 empty] | Fail | 0
[5 empty] | Blocked | 0
PROJECT NAME:
MODULE NAME: | Analytical t |  | Total Passed | 5
EXECUTED BY: | Ali Shozab |  | Total Failed | 0
DATE: | 2024-03-08
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Analytical team lead
Signin |  | 1.open app and landing page sign in appear. 2. Enter your valid email and password. | it should accept email |  | Pass
signin with google |  | 1.open app and landing page sign in appear. 2.Click on google icon to signin with google. | it should login with google. |  | Pass
signin with facebook. |  | 1.open app and landing page sign in appear. 2.Click on facebook icon to signin with facebook. | it should login with facebook. |  | Pass
Forget Password? |  | 1.open app and landing page sign in appear. 2.Click on forget password. | Password should be reset. |  | Pass
Landing page |  | 1.After sign in. 2. Landing page screen. | It should show responsive dashboard. |  | Pass
Search text field. |  | 1.After sign in. 2. On Landing page screen search field will search the result. | It should search the required result. |  | Pass
Date Filter search |  | 1.After sign in. 2. On Landing page screen date filter search the result. | It should search the required result. |  | Pass
Total forms graph is searchable. |  | 1.After sign in. 2. On Landing page screen search total forms data. | It should search the required result. |  | Pass
Adminitration and department searchable |  | 1.After sign in. 2. On Landing page screen department choose picklist. | It should search the required result. |  | Pass
Landing page "+" sign |  | 1.After sign in. 2. On Landing page screen click "+" . | It should perform its function. |  | Pass
Notification |  | 1.After sign in. 2. On Landing page screen click notification. | It should show notifications. |  | Pass
Dashboard request. |  | 1.After sign in. 2. click on dashboard. | it should show dashboard today requests. |  | Pass
Search text field. |  | 1.After sign in. 2. On dashboard screen search field will search the result. | It should search the required result. |  | Pass
Dashboard approved request. |  | 1.After sign in. 2. click on dashboard. | it should show dashboard approved requests. |  | Pass
Dashboard pending request. |  | 1.After sign in. 2. click on pending dashboard requests. | it should show dashboard pending requests. |  | Pass
Dashboard rejected request. |  | 1.After sign in. 2. click on rejected dashboard requests. | it should show dashboard rejected requests. |  | Pass
Dashboard request view form. |  | 1.After sign in. 2. click on today dashboard requests. 3. View details. | it should show form details. |  | Pass
Dashboard accept request. |  | 1.After sign in. 2. click on today dashboard requests. 3. View details. 4. click on accept button. | it should accept request and pop up menu appear Dashboard request approved. |  | Pass
Dashboard reject form |  | 1.After sign in. 2. click on today dashboard requests. 3. View details. 4. click on reject button. | it should rejectt request and pop up menu appear Dashboard request rejected and enter reason or click on send. |  | Pass

## User flow
[5 empty] | Untested | 0
[5 empty] | Pass | 18
[5 empty] | Fail | 0
[5 empty] | Blocked | 0
PROJECT NAME:
MODULE NAME: | User Flow |  | Total Passed | 5
EXECUTED BY: | Ali Shozab |  | Total Failed | 0
DATE: | 2024-03-08
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
User Flow
Fill form in sign in. |  | 1.open app and landing page sign up appear. 2. Enter your infrormation. | it should fill the form and rejister. |  | Pass
rejister with google |  | 1.open app and landing page sign up appear. 2. Enter google to rejister with it. | it should rejistered as a user. |  | Pass
rejister with facebook. |  | 1.open app and landing page sign up appear. 2. Enter facebook to rejister with it. | it should rejistered as a user. |  | Pass
forget password? |  | 1. click on forget password and and enter followeing details. | it should rejister as a user. and password will be reset. |  | Pass
today Assign tasks. |  | 1.After sign in. 2. click on today assign tasks. | it should show today assign tasks. |  | Pass
pending tasks |  | 1.After sign in. 2. click on pending assign tasks. | it should show pending assign tasks. |  | Pass
completed tasks. |  | 1.After sign in. 2. click on compeleted assign tasks. | it should show compeleted assign tasks |  | Pass
view task detail and selection. |  | 1.After sign in. 2. click assign tasks. | it should accept,pending and cancel the request.. |  | Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass