## SignUp
[5 empty] | Untested | 0
[5 empty] | Pass | 8
[5 empty] | Fail | 0
[5 empty] | Blocked | 0
PROJECT NAME: | Feedback
MODULE NAME: | Signup |  | Total Passed | 5
EXECUTED BY: | Ali Shozab |  | Total Failed | 0
DATE: | 2024-07-29
Signup as Patient
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Sign up error |  | When we logout and want to sign up | it will sign up | it will show white black pop up | Pass | done
phone no validation |  |  |  |  | Pass
resend OTP |  |  |  | Error "403" | Pass
Pass
Signup as Therapist
Pass
Pass
Pass
Pass

## Sign In
[5 empty] | Untested | 0
[5 empty] | Pass | 19
[5 empty] | Fail | 0
[5 empty] | Blocked | 0
PROJECT NAME: | Feedback
MODULE NAME: |  |  | Total Passed | 5
EXECUTED BY: |  |  | Total Failed | 0
DATE:
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass
Pass

## Home
[5 empty] | Untested | 1
[5 empty] | Pass | 1
[5 empty] | Fail | 3
[5 empty] | Blocked | 0
PROJECT NAME: | Feedback
MODULE NAME: | Home |  | Total Passed | 1
EXECUTED BY: | Ali Shozab |  | Total Failed | 0
DATE: | 2024-07-11
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Booking as Patient
Search Iqra from search bar |  | 1.Type Iqra on search bar to book appointment | Iqra profile should display | It will not display | Fail | It display result of loaded dr's profile but it has to show all searched therapist data. | done
Search Shaheer Shahid from search bar |  | 1.Type Shaheer Shahid on search bar to book appointment | Shaheer Shahid profile should display | It will not display | Fail | It display result of loaded dr's profile but it has to show all searched therapist data. | done
Go on Home Page |  | 1.click on side bar which is right side to search bar. 2. Select manage profile. | Manage profile should open | it will open and it has spelling mistake of "Description" | Fail |  | done
Go on Home Page |  | 1.click on side bar which is right side to search bar. 2. Select manage schedule and therapis select "Full day off" | On patient side,patient should not able to select time slot | On patient side,patient will able to select time slot | Pass |  | done
Untested

## Booking
[5 empty] | Untested | 10
[5 empty] | Pass | 7
[5 empty] | Fail | 2
[5 empty] | Blocked | 0
PROJECT NAME: | Feedback
MODULE NAME: | Booking
EXECUTED BY: | Ali Shozab
DATE: | 2024-07-11
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Booking as Patient
Appointment cannot be resheduled |  | 1.Click on booking button. 2.Upcoming appointment with therapist will show here. 3. Click Reshedule the appointment from there on any given date and time. | It should reshedule the appoitment. | it will show error message "The selected time slot is outside the therapist working hour" | Pass | It should has to rescheduled the appointment given slot. | done
Appointment rejistered on yesterday | https://documentviewer.herokuapp.com/?state=%7B%22ids%22:%5B%22156pgk_BKLk6s9BVipcu_rSa0G4gCoHii%22%5D,%22action%22:%22open%22,%22resourceKeys%22:%7B%7D%7D | 1.Click on booking button. 2.Slect previous date appointment. | It should not selected | it will show time slot and be selected | Fail
Booking as Therapist
open today appointments |  | 1.Click today appointments. 2.Select appointment details. 3. Select schedule appointment. | It should go to next screen to reschedule the appointment. | Schedule next appoint button will not working and spelling mistake as well. | Pass |  | done
open pending appointments |  | 1.Click pending appointment. 2. Select pending appointment details of patient.. | It should show reschedule appointment option from there. | It will show only patient details. | Pass | Reschedule button will there to give time slot to pending appointment patients. | done
open today appointments |  | 1.Click today appointments. 2.See recent patient appointment details. | It Should show Accurate details of patients and time slot. | it will show time on patient card and more details are different. | Pass | i select time 2:50pm from patient login from tayyab therapist.when i check from tayyab therapist login open today appointment time shows 7:50pm and when i open more details and there patient appointment time was accurate as 2:50pm.there is difference between time on patient card and patient card details. | done
open today appointments |  | 1.Click today appointments. 2.See recent patient appointment details and mark as completed | it should show go to complete appointment. | complete appointment button not workingand it shows error "Request failed with status code 404" | Pass |  | done
therapist mark as full day off |  | 1.click on menu left side of search bar. 2. select manage from there and mark as full day off | patient should not book any slot on that day | patient will book any slot on that day | Pass |  | done
therapist mark as completed |  | 1. Click on today appointments. 2.See patient details and click on complete appointment. | it should be completed | it will show error message 404 | Pass |  | done
Untested
Booking as Admin
admin search the therapist from therapist module. |  | 1. Click on therapist and type rejistered therapist name. | it should show required searched therapist from all therapist. | it will not show required result. | Fail |  | done
Untested
Untested
Untested
Untested
Untested
Untested
Untested
Untested
Untested

## Notification
[5 empty] | Untested | 0
[5 empty] | Pass | 13
[5 empty] | Fail | 1
[5 empty] | Blocked | 0
PROJECT NAME: | Feedback
MODULE NAME: | Notification |  | Total Passed | 4
EXECUTED BY: | Ali Shozab |  | Total Failed | 0
DATE: | 2024-07-11
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Notification as Patient
Notification 15 mints before appointment |  | 1.click on notification | 15 mints alert notification should appear | 15 mints alert notification will not appear | Fail
therapist send appointment to pending |  | 1.click on notification | Patient should recieve pending appointment | Patient will not recieve pending appointment | Pass | done
push up notification |  | 1.see on mobile notification bar | Patient should recieve any notification from therapist can see from mobile notification bar | Patient will not see any notification from therapist can see from mobile notification bar | Pass | done
Pass
Pass
Pass
Pass
Notification as Therapist
pending apointment |  | 1. Click on today appointments . 2. Select Appointment details if therapist send as pending. | Patient should recieve notification | Patient will not recieved notification | Pass | done
push up notification |  | 1.see on mobile notification bar | Therapist should recieve any notification from patient can see from mobile notification bar | Therapist will not see any notification from therapist can see from mobile notification bar | Pass | done
Mark all as read |  | 1. click on notification. 2. click on mark all as read | all notification should be read | all notification will not mark as read | Pass
Pass
Pass
Pass
Pass

## Profile
[5 empty] | Untested | 0
[5 empty] | Pass | 3
[5 empty] | Fail | 2
[5 empty] | Blocked | 0
PROJECT NAME:
MODULE NAME: |  |  | Total Passed | 3
EXECUTED BY: |  |  | Total Failed | 1
DATE:
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Profile image | upload image from camera | 1.Click Profile. 2. Open profile edit. 3. User want to change profile picture from camera. | profile picture should same as captured | profile picture will not same as captured. | Fail | vertical captured picture will to show in horizontal and horizontal captured picture will show in vertical | done
Profile image | upload image from gallery | 1.Click Profile. 2. Open profile edit. 3. User want to change profile picture from gallery. | profile picture should same as selected from gallery | when select picture from gallery. It will show selected picture | Pass | Error message appear "Request failed with status code 403" on device.i use other device for testing it is showing accurate result. | done
Password Manage |  | 1.Click Profile. 2. Open Password Manage enter old and new password. | it should accept old password and accept new password. | while creating account i entered password in alphabets and now i want to change password there is no option to enter password in alphabets. | Fail | only accept numeric password from patient and therapist profile.
Help Center |  | 1.Click Profile. 2. open help center to see FAQ'S and Contact us | it should show FAQ'S and Contact us data. | done | Pass |  | done
Privacy Policy |  | 1.Click Profile. 2. open privacy policy | It should show privacy policy | done | Pass |  | done
Pending

## Patient History in Therapy logi
[5 empty] | Untested | 0
[5 empty] | Pass | 1
[5 empty] | Fail | 1
[5 empty] | Blocked | 4
PROJECT NAME: | Feedback
MODULE NAME: | Patient History in Therapy login Module |  | Total Passed | 1
EXECUTED BY: | Ali Shozab |  | Total Failed | 1
DATE: | 2024-07-11
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Patient History |  | 1.Click on patient history | it should show patient history | it will show error "Cannot read property 'count' of undefined" | Pass | done
Fail
Blocked
Blocked
Blocked
Blocked

## Admin Module login
[5 empty] | Untested | 1
[5 empty] | Pass | 2
[5 empty] | Fail | 3
[5 empty] | Blocked | 0
PROJECT NAME: | Feedback
MODULE NAME: | Patient History in Therapy login Module |  | Total Passed | 2
EXECUTED BY: | Ali Shozab |  | Total Failed | 2
DATE: | 2024-07-11
Test Scenario | Test Data | Test Steps | Expected Result | Actual Result |  | Comments (If any) | Dev Comments
Payment history |  | 1.Click on payment.2.click on transaction and filter required data | it should show payment history | it will show error " Fetching payment data" | Fail
Payment history |  | 1.Click on payment.2.click on summary and select debit or credit card | it should show payment history | it will show error " Fetching payment data" | Fail
Payment history PDF |  | 1.Click on payment.2.click on export as PDF | it should export pdf file | it will not export pdf file | Fail
current password |  | 1.click on profile. 2. After login with new password. Current password field show old password after new password login. | it should show updated password | it will not show updated password | Pass
New password |  | 1.click on profile. 2. After login and select passwords. 3. admin change password with new password use old keywords. | it should show error "old and new password should not be same" | it is accepting | Pass
Untested